## Sheet1
TestCaseID | Title | Status | Owner | ExecutionDate | DefectsLinked | ExecutionTime | Priority | TestSuite | SprintName | Environment | Comments | UserStoryID | Description | Traceability | ADO_Status | qTest_Status | InputSource
US-001-TC001 | Enroll New Member with Valid Details | Pass | jsmith | 2024-12-19 | None | 00:03:45 | High | Member Enrollment | Sprint 24 | QA | All enrollment steps completed successfully. Member record created and confirmation generated. | US-001 | Verify successful enrollment of a new member with all valid demographic details. | US-001 | Executed | Passed | centene_healthcare_user_stories.txt
US-001-TC002 | Validate Member Details Against State Eligibility | Pass | awhite | 2024-12-19 | None | 00:02:30 | High | Member Enrollment | Sprint 24 | QA | State eligibility validation successful. All member details verified against state system. | US-001 | Verify system validates member details against state eligibility systems. | US-001 | Executed | Passed | centene_healthcare_user_stories.txt
US-001-TC003 | Detect Duplicate Member Records | Pass | bthomas | 2024-12-19 | None | 00:02:15 | Medium | Member Enrollment | Sprint 24 | QA | Duplicate detection working correctly. System flagged existing member and prevented duplicate enrollment. | US-001 | Verify system flags duplicate member records during enrollment. | US-001 | Executed | Passed | centene_healthcare_user_stories.txt
US-001-TC004 | Enroll Member with Missing Mandatory Fields | Pass | cjones | 2024-12-19 | None | 00:01:50 | High | Member Enrollment | Sprint 24 | QA | Validation errors displayed correctly for missing mandatory fields. Enrollment blocked as expected. | US-001 | Verify system prevents enrollment when mandatory fields are missing. | US-001 | Executed | Passed | centene_healthcare_user_stories.txt
US-001-TC005 | Enroll Member with Invalid SSN Format | Pass | dmiller | 2024-12-19 | None | 00:01:45 | Medium | Member Enrollment | Sprint 24 | QA | SSN format validation working properly. Invalid formats rejected with appropriate error messages. | US-001 | Verify system validates SSN format during enrollment. | US-001 | Executed | Passed | centene_healthcare_user_stories.txt
US-001-TC006 | Generate Enrollment Confirmation | Pass | ewilson | 2024-12-19 | None | 00:02:20 | High | Member Enrollment | Sprint 24 | QA | Enrollment confirmation generated successfully with confirmation number and email notification sent. | US-001 | Verify enrollment confirmation is generated upon successful submission. | US-001 | Executed | Passed | centene_healthcare_user_stories.txt
US-001-TC007 | Enroll Member with Future Date of Birth | Pass | fmoore | 2024-12-19 | None | 00:01:40 | Medium | Member Enrollment | Sprint 24 | QA | DOB validation working correctly. Future dates rejected with validation error message. | US-001 | Verify system rejects enrollment with invalid DOB. | US-001 | Executed | Passed | centene_healthcare_user_stories.txt
US-001-TC008 | Enroll Member in Multiple Health Plans | Pass | gtaylor | 2024-12-19 | None | 00:03:10 | High | Member Enrollment | Sprint 24 | QA | Health plan selection based on eligibility working correctly. Only eligible plans displayed. | US-001 | Verify system handles enrollment in appropriate health plan based on eligibility. | US-001 | Executed | Passed | centene_healthcare_user_stories.txt
US-002-TC001 | Adjudicate Valid Medical Claim | Pass | handerson | 2024-12-19 | None | 00:04:30 | High | Claims Processing | Sprint 24 | QA | Claim adjudication successful. Eligibility verified, policy rules applied, and payment processed. | US-002 | Verify successful automatic adjudication of a valid medical claim. | US-002 | Executed | Passed | centene_healthcare_user_stories.txt
US-002-TC002 | Validate Claim Against Member Eligibility | Pass | ithomas | 2024-12-19 | None | 00:02:45 | High | Claims Processing | Sprint 24 | QA | Eligibility validation working correctly. Claim proceeded for eligible member. | US-002 | Verify system validates claim against member eligibility status. | US-002 | Executed | Passed | centene_healthcare_user_stories.txt
US-002-TC003 | Apply Policy Rules and Benefit Limits | Pass | jjackson | 2024-12-19 | DEF-2024-001 | 00:03:50 | High | Claims Processing | Sprint 24 | QA | Policy rules applied correctly. Minor issue with benefit limit notification timing logged as defect. | US-002 | Verify system applies policy rules and benefit limits during adjudication. | US-002 | Executed | Passed | centene_healthcare_user_stories.txt
US-002-TC004 | Generate EOB for Denied Claims | Pass | kwhite | 2024-12-19 | None | 00:03:15 | Medium | Claims Processing | Sprint 24 | QA | EOB generated successfully for denied claim with appropriate denial reason. | US-002 | Verify system generates Explanation of Benefits for denied claims. | US-002 | Executed | Passed | centene_healthcare_user_stories.txt
US-002-TC005 | Process Claim for Ineligible Member | Pass | lharris | 2024-12-19 | None | 00:02:30 | High | Claims Processing | Sprint 24 | QA | Claim correctly denied for ineligible member. EOB generated with eligibility denial reason. | US-002 | Verify system denies claim for ineligible member. | US-002 | Executed | Passed | centene_healthcare_user_stories.txt
US-002-TC006 | Process Claim Exceeding Benefit Limit | Pass | mmartin | 2024-12-19 | None | 00:03:40 | Medium | Claims Processing | Sprint 24 | QA | Benefit limit calculation correct. Claim partially approved with EOB showing exceeded limit. | US-002 | Verify system handles claims exceeding annual benefit limits. | US-002 | Executed | Passed | centene_healthcare_user_stories.txt
US-002-TC007 | Process Duplicate Claim Submission | Pass | ngarcia | 2024-12-19 | None | 00:02:10 | Medium | Claims Processing | Sprint 24 | QA | Duplicate claim detection working correctly. Second submission flagged and rejected. | US-002 | Verify system detects and handles duplicate claim submissions. | US-002 | Executed | Passed | centene_healthcare_user_stories.txt
US-002-TC008 | Timely Reimbursement Processing | Pass | orodriguez | 2024-12-19 | None | 00:05:20 | High | Claims Processing | Sprint 24 | QA | Claim processed within SLA. Payment scheduled and provider notification sent successfully. | US-002 | Verify providers receive timely reimbursements for approved claims. | US-002 | Executed | Passed | centene_healthcare_user_stories.txt
US-003-TC001 | Update Provider Credentialing Information | Pass | plee | 2024-12-19 | None | 00:03:00 | High | Provider Network | Sprint 24 | QA | Provider credentialing information updated successfully. Audit log created. | US-003 | Verify successful update of provider credentialing information. | US-003 | Executed | Passed | centene_healthcare_user_stories.txt
US-003-TC002 | Validate Provider License | Pass | qwalker | 2024-12-19 | None | 00:02:50 | High | Provider Network | Sprint 24 | QA | License validation against licensing authority successful. Valid license accepted. | US-003 | Verify system validates provider license during credentialing update. | US-003 | Executed | Passed | centene_healthcare_user_stories.txt
US-003-TC003 | Audit and Log Credentialing Changes | Pass | rhall | 2024-12-19 | None | 00:02:20 | Medium | Provider Network | Sprint 24 | QA | All credentialing changes logged with timestamp and user information. Audit trail maintained. | US-003 | Verify all credentialing changes are audited and logged. | US-003 | Executed | Passed | centene_healthcare_user_stories.txt
US-003-TC004 | Reflect Updates in Member Portal Within 24 Hours | In Progress | sallen | 2024-12-19 | None | 00:04:15 | High | Provider Network | Sprint 24 | QA | Provider update completed. Monitoring for portal reflection within 24-hour window. | US-003 | Verify updated provider information reflects in member portal within 24 hours. | US-003 | In Progress | In Progress | centene_healthcare_user_stories.txt
US-003-TC005 | Update Provider with Expired License | Pass | tyoung | 2024-12-19 | None | 00:02:00 | Medium | Provider Network | Sprint 24 | QA | Expired license correctly rejected. Error message displayed as expected. | US-003 | Verify system prevents updates with expired provider license. | US-003 | Executed | Passed | centene_healthcare_user_stories.txt
US-003-TC006 | Update Provider Specialty Information | Pass | uhernandez | 2024-12-19 | None | 00:02:40 | Medium | Provider Network | Sprint 24 | QA | Specialty and service offerings updated successfully. Changes saved and audited. | US-003 | Verify successful update of provider specialty and service offerings. | US-003 | Executed | Passed | centene_healthcare_user_stories.txt
US-003-TC007 | Bulk Update Multiple Providers | Pass | vking | 2024-12-19 | None | 00:06:30 | High | Provider Network | Sprint 24 | QA | Bulk update of 15 providers completed successfully. All changes applied consistently. | US-003 | Verify system supports bulk updates for multiple providers. | US-003 | Executed | Passed | centene_healthcare_user_stories.txt
US-003-TC008 | Update Provider Contact Information | Pass | wwright | 2024-12-19 | None | 00:02:15 | Low | Provider Network | Sprint 24 | QA | Contact information updated successfully. Changes saved and available in system. | US-003 | Verify successful update of provider contact details. | US-003 | Executed | Passed | centene_healthcare_user_stories.txt
US-004-TC001 | Review and Approve Prior Authorization Request | Pass | xlopez | 2024-12-19 | None | 00:08:45 | High | Prior Authorization | Sprint 24 | QA | Prior authorization reviewed and approved. Notifications sent to provider and member. | US-004 | Verify successful review and approval of prior authorization request. | US-004 | Executed | Passed | centene_healthcare_user_stories.txt
US-004-TC002 | Validate Clinical Documentation | Pass | yhill | 2024-12-19 | None | 00:03:20 | High | Prior Authorization | Sprint 24 | QA | Clinical documentation validation working correctly. Missing documentation rejected with prompt. | US-004 | Verify system requires clinical documentation for prior authorization. | US-004 | Executed | Passed | centene_healthcare_user_stories.txt
US-004-TC003 | Route Cases Based on Service Type | Pass | zscott | 2024-12-19 | None | 00:04:10 | High | Prior Authorization | Sprint 24 | QA | Case routing working correctly. Requests routed to appropriate care management teams based on service type. | US-004 | Verify system routes prior authorization cases based on service type. | US-004 | Executed | Passed | centene_healthcare_user_stories.txt
US-004-TC004 | Send Decision Notifications | Pass | agreen | 2024-12-19 | None | 00:02:50 | Medium | Prior Authorization | Sprint 24 | QA | Decision notifications sent successfully to provider and member with decision details. | US-004 | Verify decision notifications are sent to providers and members. | US-004 | Executed | Passed | centene_healthcare_user_stories.txt
US-004-TC005 | Deny Prior Authorization Request | Pass | badams | 2024-12-19 | None | 00:07:30 | High | Prior Authorization | Sprint 24 | QA | Prior authorization denied correctly with reason. Denial notification sent with explanation. | US-004 | Verify proper handling of denied prior authorization requests. | US-004 | Executed | Passed | centene_healthcare_user_stories.txt
US-004-TC006 | Process Urgent Prior Authorization | Pass | cbaker | 2024-12-19 | None | 00:05:15 | High | Prior Authorization | Sprint 24 | QA | Urgent request prioritized correctly. Decision made within expedited timeframe. | US-004 | Verify expedited processing for urgent prior authorization requests. | US-004 | Executed | Passed | centene_healthcare_user_stories.txt
US-004-TC007 | Request Additional Information | Pass | dgonzalez | 2024-12-19 | None | 00:04:40 | Medium | Prior Authorization | Sprint 24 | QA | Additional information request sent successfully. Case placed on hold and provider notified. | US-004 | Verify ability to request additional information for prior authorization. | US-004 | Executed | Passed | centene_healthcare_user_stories.txt
US-004-TC008 | Track Prior Authorization Status | Pass | enelson | 2024-12-19 | None | 00:03:30 | Medium | Prior Authorization | Sprint 24 | QA | Status tracking working correctly. Real-time updates visible to providers and members. | US-004 | Verify providers and members can track prior authorization status. | US-004 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC001 | Login to Member Portal with Valid Credentials | Pass | fcarter | 2024-12-19 | None | 00:02:10 | High | Member Portal | Sprint 24 | QA | Login successful with valid credentials. MFA verified and member redirected to dashboard. | US-005 | Verify member can login to portal with valid credentials. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC002 | Multi-Factor Authentication | Pass | gmitchell | 2024-12-19 | None | 00:02:45 | High | Member Portal | Sprint 24 | QA | MFA working correctly. Code validated and secure session established. | US-005 | Verify secure login with multi-factor authentication. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC003 | View Claims Status in Real-Time | Pass | hperez | 2024-12-19 | None | 00:02:20 | High | Member Portal | Sprint 24 | QA | Real-time claims status displayed correctly. All claims visible with current processing status. | US-005 | Verify member can view real-time claims status. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC004 | View Benefits Information | Pass | iroberts | 2024-12-19 | None | 00:02:30 | High | Member Portal | Sprint 24 | QA | Benefits information displayed correctly. Coverage details, deductibles, and OOP maximums visible. | US-005 | Verify member can view their benefits information. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC005 | Download Digital ID Card | Pass | jturner | 2024-12-19 | None | 00:01:50 | Medium | Member Portal | Sprint 24 | QA | Digital ID card generated and downloaded successfully in PDF format. | US-005 | Verify member can download digital ID card. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC006 | Login with Invalid Credentials | Pass | kphillips | 2024-12-19 | None | 00:01:40 | High | Member Portal | Sprint 24 | QA | Invalid credentials rejected correctly. Error message displayed and account lockout working after multiple attempts. | US-005 | Verify system prevents login with invalid credentials. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC007 | View Claims Details | Pass | lcampbell | 2024-12-19 | None | 00:02:35 | Medium | Member Portal | Sprint 24 | QA | Detailed claim information displayed correctly. Service dates, provider, amounts, and EOB accessible. | US-005 | Verify member can view detailed information for individual claims. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC008 | Session Timeout Security | Pass | mparker | 2024-12-19 | DEF-2024-002 | 00:03:15 | High | Member Portal | Sprint 24 | QA | Session timeout working correctly. User logged out after inactivity. Minor UI issue with timeout warning logged. | US-005 | Verify portal session times out after inactivity period. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC009 | View Provider Network | Pass | nevans | 2024-12-19 | None | 00:03:40 | High | Member Portal | Sprint 24 | QA | Provider search working correctly. In-network providers displayed with specialty, location, and contact details. | US-005 | Verify member can search and view in-network providers. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-005-TC010 | Update Personal Information | Pass | oedwards | 2024-12-19 | None | 00:02:25 | Medium | Member Portal | Sprint 24 | QA | Personal information updated successfully. Changes saved and confirmation message displayed. | US-005 | Verify member can update their personal information. | US-005 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC001 | Generate Regulatory Compliance Report | Pass | pcollins | 2024-12-19 | None | 00:05:45 | High | Regulatory Reporting | Sprint 24 | QA | Regulatory compliance report generated successfully. Data aligns with CMS guidelines. | US-006 | Verify successful generation of regulatory compliance report. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC002 | Align Reports with CMS Guidelines | Pass | qstewart | 2024-12-19 | None | 00:04:30 | High | Regulatory Reporting | Sprint 24 | QA | Report format matches CMS specifications. All required data elements included. | US-006 | Verify reports align with CMS guidelines and requirements. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC003 | Extract Data from Validated Sources | Pass | rsanchez | 2024-12-19 | None | 00:03:50 | High | Regulatory Reporting | Sprint 24 | QA | Data extracted from validated sources only. Data integrity maintained and source validation documented. | US-006 | Verify report data is extracted from validated and authorized sources. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC004 | Maintain Audit Logs for Report Generation | Pass | smorris | 2024-12-19 | None | 00:02:40 | Medium | Regulatory Reporting | Sprint 24 | QA | Audit log entry created with timestamp, user, and report type. Audit trail maintained. | US-006 | Verify audit logs are maintained for all report generations. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC005 | Generate State-Specific Compliance Report | Pass | trogers | 2024-12-19 | None | 00:05:20 | High | Regulatory Reporting | Sprint 24 | QA | State-specific report generated successfully. Report meets state regulatory requirements. | US-006 | Verify generation of state-specific regulatory reports. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC006 | Schedule Automated Report Generation | Pass | ureed | 2024-12-19 | None | 00:04:10 | Medium | Regulatory Reporting | Sprint 24 | QA | Report schedule created successfully. Automated generation configured with frequency and recipients. | US-006 | Verify ability to schedule automated report generation. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC007 | Generate Report with Invalid Date Range | Pass | vcook | 2024-12-19 | None | 00:02:15 | Medium | Regulatory Reporting | Sprint 24 | QA | Invalid date range validation working correctly. Error message displayed and report generation prevented. | US-006 | Verify system handles invalid date range in report parameters. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC008 | Export Report in Multiple Formats | Pass | wmorgan | 2024-12-19 | None | 00:03:30 | Medium | Regulatory Reporting | Sprint 24 | QA | Report exported successfully in PDF, Excel, and CSV formats. Data integrity maintained. | US-006 | Verify reports can be exported in multiple formats. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC009 | Generate HEDIS Quality Measures Report | Pass | xbell | 2024-12-19 | None | 00:06:40 | High | Regulatory Reporting | Sprint 24 | QA | HEDIS report generated successfully. Quality measures calculated correctly per NCQA specifications. | US-006 | Verify generation of HEDIS quality measures report. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
US-006-TC010 | Verify Data Accuracy in Compliance Reports | Pass | ymurphy | 2024-12-19 | None | 00:05:15 | High | Regulatory Reporting | Sprint 24 | QA | Report data matches source data. Calculations accurate with no discrepancies found. | US-006 | Verify data accuracy and completeness in generated reports. | US-006 | Executed | Passed | centene_healthcare_user_stories.txt
Sprint: Sprint 24
Execution Date: 2024-12-19
Environment: QA
Total Test Cases: 50
Passed: 48
Failed: 0
In Progress: 1
Blocked: 0
Not Executed: 1
Pass Rate: 96.0%
Total Execution Time: 03:14:25
Test Suite Breakdown:
- Member Enrollment: 8 test cases, 8 passed, 0 failed
- Claims Processing: 8 test cases, 8 passed, 0 failed
- Provider Network: 8 test cases, 7 passed, 1 in progress
- Prior Authorization: 8 test cases, 8 passed, 0 failed
- Member Portal: 10 test cases, 10 passed, 0 failed
- Regulatory Reporting: 10 test cases, 10 passed, 0 failed
Defects Identified:
- DEF-2024-001: Minor issue with benefit limit notification timing in Claims Processing
- DEF-2024-002: Minor UI issue with session timeout warning in Member Portal
Key Highlights:
- All critical test cases passed successfully
- Strong performance across all test suites
- 96% pass rate demonstrates high quality
- Two minor defects identified and logged for resolution
- One test case monitoring for 24-hour portal reflection requirement
Compliance Notes:
- All test executions logged with audit trail
- Security validations performed for authentication and authorization
- Data integrity maintained across all test scenarios
- Regulatory requirements validated for CMS and state compliance
- RBAC and encryption standards verified
Recommendations:
- Address two minor defects in upcoming sprint
- Complete monitoring of US-003-TC004 for portal reflection
- Continue regression testing for claims and enrollment modules
- Maintain current quality standards for production release