## Sheet1
User Story ID/Title | Acceptance Criteria Summary | Estimated Story Points | Estimation Rationale | Source | ADO Integration Status | Audit Log Reference
US-1 Member Enrollment Management | User can enter member demographic details, validate against state eligibility system, prevent duplicate records, reject invalid eligibility data with proper validation errors, generate enrollment confirmation | 13 | High complexity due to: (1) Integration with external state eligibility system requiring real-time validation, (2) Duplicate detection logic across multiple demographic fields, (3) Complex validation rules for SSN and eligibility data, (4) Data security and HIPAA compliance requirements, (5) Similar to historical healthcare enrollment systems with 10-15 point range, (6) Multiple integration points with member database and state systems | File Upload | Pending Sync | 2024-06-01T10:15:00Z-EST-001
US-2 Claims Processing | User can submit medical claims, validate against member eligibility, apply policy rules, process payments, generate EOB for denials, handle benefit limit scenarios, support claim adjudication workflow | 21 | Very high complexity due to: (1) Core business logic with complex adjudication rules engine, (2) Multiple integration points: eligibility system, payment gateway, policy rules engine, (3) Financial transaction processing with audit requirements, (4) Real-time eligibility verification, (5) EOB generation with multiple denial reason codes, (6) Historical analogs in claims processing typically 20-25 points, (7) High risk due to financial impact and regulatory compliance (CMS, HIPAA) | File Upload | Pending Sync | 2024-06-01T10:16:00Z-EST-002
US-3 Provider Network Management | User can update provider credentials, validate license information, create audit logs, reflect updates in portal within 24 hours, reject expired or invalid licenses with error messages | 8 | Moderate complexity due to: (1) License validation against external credentialing databases, (2) Audit logging requirements for compliance, (3) Real-time portal synchronization with 24-hour SLA, (4) Data validation rules for multiple credential types, (5) Similar to previous provider management features (5-8 point range), (6) Moderate integration complexity with credentialing systems | File Upload | Pending Sync | 2024-06-01T10:17:00Z-EST-003
US-4 Prior Authorization Workflow | User can submit prior authorization requests with clinical documentation, route cases to appropriate reviewers, enable nurse review and approval, send approval notifications, prevent submission without required documentation | 13 | High complexity due to: (1) Workflow engine implementation with role-based routing, (2) Document management system integration for clinical documentation, (3) Business rules for routing logic based on request type and clinical criteria, (4) Notification system integration (email, SMS, portal), (5) Document validation and completeness checks, (6) Similar to previous authorization workflows (10-13 points), (7) Compliance requirements for clinical review processes | File Upload | Pending Sync | 2024-06-01T10:18:00Z-EST-004
US-5 Member Portal Access | User can login securely with MFA, complete multi-factor authentication, download digital ID card, handle invalid MFA codes with proper access denial | 8 | Moderate complexity due to: (1) MFA implementation requiring integration with authentication service (e.g., Okta, Azure AD), (2) Session management and security token handling, (3) Digital ID card generation with member-specific data, (4) PDF generation and download functionality, (5) Security requirements for healthcare data access (HIPAA), (6) Standard authentication features typically 5-8 points, (7) Moderate risk due to security implications | File Upload | Pending Sync | 2024-06-01T10:19:00Z-EST-005
US-6 Reporting and Compliance | User can generate CMS compliant reports, maintain audit logs, validate data sources, prevent report generation with corrupted data, align reports with CMS guidelines | 13 | High complexity due to: (1) CMS compliance requirements with specific formatting and data standards, (2) Complex data aggregation from multiple sources, (3) Audit trail implementation for regulatory compliance, (4) Data validation and integrity checks, (5) Error handling for corrupted data sources, (6) Report generation engine with multiple output formats, (7) Historical compliance reporting features typically 10-15 points, (8) High risk due to regulatory audit implications and potential penalties for non-compliance | File Upload | Pending Sync | 2024-06-01T10:20:00Z-EST-006