## Sheet1
User Story ID/Title | Acceptance Criteria Summary | Estimated Story Points | Estimation Rationale | Source | ADO Integration Status | Audit Log Reference
US1 - Member Enrollment Management | Successful enrollment, duplicate validation, invalid eligibility rejection | 8 | Complexity due to eligibility integration, duplicate checks, negative scenarios, historical analog: US1 in Medicaid Enrollment (7 points) | File Upload | Not Synced | 2024-06-01T10:15:00Z-EST-001
US2 - Claims Processing | Claim adjudication, denial for ineligible members, benefit limit enforcement | 13 | High complexity: eligibility, policy rules, multiple negative cases, integration with payment engine, historical analog: US2 in Claims Adjudication (12 points) | File Upload | Not Synced | 2024-06-01T10:15:00Z-EST-002
US3 - Provider Network Management | Credential update, invalid license rejection | 5 | Moderate complexity: credential validation, audit logging, negative scenario, historical analog: US3 in Provider Credentialing (5 points) | File Upload | Not Synced | 2024-06-01T10:15:00Z-EST-003
US4 - Prior Authorization Workflow | Approval workflow, missing documentation prevention | 8 | Workflow routing, clinical review, error handling, historical analog: US4 in Prior Auth (8 points) | File Upload | Not Synced | 2024-06-01T10:15:00Z-EST-004
US5 - Member Portal Access | Secure login with MFA, invalid MFA, ID card download | 5 | Security integration, MFA, negative scenario, digital asset download, historical analog: US5 in Portal Security (5 points) | File Upload | Not Synced | 2024-06-01T10:15:00Z-EST-005
US6 - Reporting and Compliance | CMS compliant report, invalid data source prevention | 8 | Regulatory compliance, audit logging, error handling, historical analog: US6 in Compliance Reporting (8 points) | File Upload | Not Synced | 2024-06-01T10:15:00Z-EST-006